## Sheet1
S.NO | Role | Tasks | Start Date | Start Time | Finish Date | Finish Time
1 | Administrative Officer | Daily Attendance Check | 2022-01-19 | 9.00am | 2022-01-19 | 9.30am
2 | Design team | Automate the solidworks | 2022-01-19 | 10.30am | 2022-01-22 | 5.30am
3 | Design team incharge | Conduct daily status meetiing | 2022-01-19 | 3.00pm | 2022-01-19 | 3.30pm
4 | Developer | Add a filter option in Task Manager | 2022-01-19 | 9.00pm | 2022-01-24 | 6.00pm
5 | Manual Tester | Test the new Application v2.3 | 2022-01-19 | 10.00am | 2022-01-22 | 5.30pm
6 | Automation Tester | Automate the APK using APPIUM | 2022-01-19 | 10.30am | 2022-01-20 | 7.30pm
7 | Design team incharge | Review Daily Tasks | 2022-01-19 | 6.30pm | 2022-01-19 | 7.00pm
8 | Developer team incharge | Conduct daily status meetiing | 2022-01-19 | 7.30pm | 2022-01-19 | 8.00pm
9 | Manager | Discussion about the progress | 2022-01-19 | 8.00pm | 2022-01-19 | 9.00pm